## Project Planner
XAI For Self Driving cars
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Task 01: T1 | 1 | 5 | 1 | 4 | 25%
Sub task:T1.1 | 1 | 6 | 1 | 6 | 100%
Sub task:T1.2 | 2 | 4 | 2 | 5 | 35%
Sub task:T1.3 | 4 | 8 | 4 | 6 | 10%
Task 01: T2.0 | 4 | 2 | 4 | 8 | 85%
Sub task:T2.1 | 4 | 3 | 4 | 6 | 85%
Task 01: T3.0 | 5 | 4 | 5 | 3 | 50%
Sub task T3.1 | 5 | 2 | 5 | 5 | 60%
Sub task T3.2 | 5 | 2 | 5 | 6 | 75%
Task 01: T4.0 | 6 | 5 | 6 | 7 | 100%
Sub task T4.1 | 6 | 1 | 5 | 8 | 60%
Sub task T4.2 | 9 | 3 | 9 | 3 | 0%
Sub task T4.3 | 9 | 6 | 9 | 7 | 50%
Task 01: T5.0 | 9 | 3 | 9 | 1 | 0%
Sub task T5.1 | 9 | 4 | 8 | 5 | 1%
Task 01: T6.0 | 10 | 5 | 10 | 3 | 80%
Sub task T6.1 | 11 | 2 | 11 | 5 | 0%
Task 01: T7.0 | 12 | 6 | 12 | 7 | 0%
Sub task T7.1 | 12 | 1 | 12 | 5 | 0%
Task 01: T8.0 | 14 | 5 | 14 | 6 | 0%
Sub task T8.1 | 14 | 8 | 14 | 2 | 44%
Task 01: T9.0 | 14 | 7 | 14 | 3 | 0%
Sub task T9.1 | 15 | 4 | 15 | 8 | 12%
Task 01: T10.0 | 15 | 5 | 15 | 3 | 5%
Sub task T10.1 | 15 | 8 | 15 | 5 | 0%

## Task descriptions
Tasks | Description
Task 01: T1.0 | Survey of the existing work in XAI (Especially from UC Berkley).
Sub task:T1.1 | Survey of the existing work in XAI from UC Berkley
Sub task:T1.2 | Survey of the existing other work in XAI from Authors of main reference
Sub task:T1.3 | Survey of the existing other work in XAI
Task 01: T2.0 | Set up google Colab to use the free available resources.
Sub task:T2.1 | Setup and test using a small example jupyter notebook
Task 01: T3.0 | Train a convolutional network end-to-end (from images to angles).
Sub task T3.1 | Run existing implementation with the trained weights if given
Sub task T3.2 | If not, train the network using the BDD datset from UCB
Task 01: T4.0 | Test it on existing data. Record the causal explanations.
Sub task T4.1 | demonstrate a test explanation on test data
Sub task T4.2 | Seperate the textual explanation and visual explantion part
Sub task T4.3 | Attempt only visual explanation
Task 01: T5.0 | Setup CARLA to take inputs from the trained networks and show the explanation.
Sub task T5.1
Task 01: T6.0 | Use the already trained network in CARLA to drive car autonomously and compare the results.
Sub task T6.1
Task 01: T7.0 | Build a real-time demonstrator that highlights the attention leading to result.
Sub task T7.1
Task 01: T8.0 | Build a real-time demonstrator that highlights the attention leading to result.
Sub task T8.1
Task 01: T9.0 | (Optional) Record dataset to train on CARLA.
Sub task T9.1
Task 01: T10.0 | (Optional) Unfreeze last layers of the network and retrain the network on CARLA dataset.
Sub task T10.1